# Task Breakdown - Monitor Traffic CCTV Jogja

Infrastruktur dan Platform Big Data - Semester 4

Timeline: 1 Minggu (7 Hari)

## Legenda Prioritas

HIGH - Wajib selesai, core pipeline

MEDIUM - Penting, tapi bisa menyusul

LOW - Enhancement, kalau ada waktu

# NAD - Data Pipeline & Infrastruktur

## Day 1: Kafka Setup

| No | Task | File | Prioritas | Estimasi |
| --- | --- | --- | --- | --- |
| 1 | Implementasi Kafka producer: kirim data traffic ke topic traffic-events setiap 5 detik | src/kafka/producer.py | HIGH | 2 jam |
| 2 | Implementasi Kafka consumer: baca dari topic traffic-alerts untuk trigger notifikasi | src/kafka/consumer.py | HIGH | 1.5 jam |
| 3 | Implementasi poller: ambil data dari CSV/PostgreSQL periodik, publish ke Kafka | src/ingestion/poller.py | HIGH | 2 jam |
| 4 | Setup Kafka topics di script init | scripts/init_kafka_topics.sh | MEDIUM | 30 menit |

Cekpoint Day 1: Kafka producer bisa kirim data dummy, consumer bisa baca.

## Day 2-3: Spark Streaming (Core Pipeline)

| No | Task | File | Prioritas | Estimasi |
| --- | --- | --- | --- | --- |
| 5 | Query 1 - Traffic count: hitung jumlah kendaraan per menit dari Kafka stream | src/spark/streaming/traffic_count_query.py | HIGH | 2.5 jam |
| 6 | Query 2 - Density: hitung kepadatan (total / area) per kamera | src/spark/streaming/density_query.py | HIGH | 2 jam |
| 7 | Query 3 - Alert: deteksi anomali > threshold, publish ke topic traffic-alerts | src/spark/streaming/alert_query.py | HIGH | 2 jam |
| 8 | Query 4 - Aggregation: agregasi data per 5 menit (min, max, avg count) | src/spark/streaming/aggregation_query.py | HIGH | 2 jam |

Cekpoint Day 2-3: Semua query bisa jalan di Spark Structured Streaming, output ke console/Kafka.

## Day 3-4: Spark Batch

| No | Task | File | Prioritas | Estimasi |
| --- | --- | --- | --- | --- |
| 9 | Analisis kepadatan per jam dari data historis PostgreSQL | src/spark/batch/hourly_density.py | HIGH | 2 jam |
| 10 | Analisis peak hour: jam dengan kepadatan tertinggi per kamera | src/spark/batch/peak_hour_analysis.py | HIGH | 1.5 jam |
| 11 | Tren mingguan: perbandingan kepadatan hari-ke-hari | src/spark/batch/weekly_trend.py | MEDIUM | 1.5 jam |
| 12 | Weekday vs Weekend: perbandingan pola kepadatan | src/spark/batch/weekday_weekend.py | MEDIUM | 1.5 jam |
| 13 | Input data untuk ML: export data agregat dari PostgreSQL ke format siap ML | src/spark/batch/prediction_input.py | MEDIUM | 1 jam |

Cekpoint Day 3-4: Semua batch job bisa jalan manual via spark-submit, output terlihat.

## Day 4-5: Airflow + Docker + Monitoring

| No | Task | File | Prioritas | Estimasi |
| --- | --- | --- | --- | --- |
| 14 | DAG 1 - Daily batch: trigger Spark batch job setiap hari jam 00:00 | src/airflow/dags/daily_batch.py | HIGH | 2 jam |
| 15 | DAG 2 - Weekly ML retrain: trigger ML retrain setiap Minggu | src/airflow/dags/weekly_ml_retrain.py | HIGH | 1.5 jam |
| 16 | DAG 3 - Health check: cek service tiap 30 menit, alert kalau ada down | src/airflow/dags/pipeline_health_check.py | MEDIUM | 2 jam |
| 17 | Update Dockerfiles sesuai kebutuhan tiap service | docker/*/Dockerfile | MEDIUM | 1 jam |
| 18 | Update script setup + init kafka/minio | scripts/*.sh | LOW | 1 jam |

Cekpoint Day 4-5: Airflow webserver bisa diakses, DAG trigger manual sukses.

## Day 5-6: Monitoring + Unit Test

| No | Task | File | Prioritas | Estimasi |
| --- | --- | --- | --- | --- |
| 19 | Prometheus config: scrape target (Kafka, Spark, App, PostgreSQL) | src/monitoring/prometheus/prometheus.yml | MEDIUM | 1.5 jam |
| 20 | Alert rules: threshold kepadatan, service down, Kafka lag | src/monitoring/prometheus/alert_rules.yml | MEDIUM | 1.5 jam |
| 21 | Loki config: collect logs dari semua container | src/monitoring/loki/loki-config.yml | LOW | 1 jam |
| 22 | Unit test detection + conftest | tests/test_detection.py, conftest.py | MEDIUM | 2 jam |

Cekpoint Day 5-6: Prometheus target all UP, Loki terima logs.

## Day 7: Integrasi + Debug + Push

| No | Task | Prioritas |
| --- | --- | --- |
| 23 | Tes integrasi: main.py -> Kafka -> Spark Streaming -> PostgreSQL | HIGH |
| 24 | Debug error + fix | HIGH |
| 25 | Git commit + push | HIGH |

# TAL - Analytics, ML & Visualization

## Day 1-2: ML Pipeline (Core)

| No | Task | File | Prioritas | Estimasi |
| --- | --- | --- | --- | --- |
| 1 | K-Means Clustering: kelompokkan pola kepadatan (sepi, normal, padat, sangat padat) | src/ml/clustering.py | HIGH | 3 jam |
| 2 | Time Series Forecasting: prediksi jumlah kendaraan 1-6 jam ke depan pake Prophet/statsmodels | src/ml/forecasting.py | HIGH | 3 jam |
| 3 | Training pipeline: load data dari PostgreSQL, train model, save ke .pkl | src/ml/train.py | HIGH | 2 jam |

Cekpoint Day 1-2: Model K-Means bisa klaster data, forecasting keluarin prediksi jam depan.

## Day 2-3: Dashboard (Grafana + Metabase)

| No | Task | File | Prioritas | Estimasi |
| --- | --- | --- | --- | --- |
| 4 | Grafana dashboard JSON: 13 panel (GeoMap, timeseries, pie, bargauge, Kafka throughput, alert history) | src/dashboard/grafana/dashboards/traffic-monitor.json | HIGH | 4 jam |
| 5 | Metabase setup: koneksi ke PostgreSQL, buat dashboard interaktif ad-hoc | src/dashboard/metabase/setup.py | MEDIUM | 2 jam |

Cekpoint Day 2-3: Grafana dashboard tampil di localhost:3000, Metabase connect ke PostgreSQL.

## Day 3-4: Alerting

| No | Task | File | Prioritas | Estimasi |
| --- | --- | --- | --- | --- |
| 6 | Telegram bot: baca dari topic Kafka traffic-alerts, kirim notifikasi ke chat | src/alerting/telegram_bot.py | HIGH | 2.5 jam |
| 7 | Email notifier: kirim alert via SMTP untuk kepadatan > threshold | src/alerting/email_notifier.py | MEDIUM | 2 jam |

Cekpoint Day 3-4: Telegram bot kirim pesan test, email terkirim.

## Day 4-5: Security + Governance

| No | Task | File | Prioritas | Estimasi |
| --- | --- | --- | --- | --- |
| 8 | RBAC: 4 role (admin, analyst, viewer, operator) - validasi akses | src/security/rbac.py | MEDIUM | 2 jam |
| 9 | Credential manager: load secrets dari env, validasi required vars | src/security/credential_manager.py | MEDIUM | 1 jam |
| 10 | Data lineage: track asal data (YouTube->Kafka->Spark->PostgreSQL), simpan ke tabel data_lineage | src/governance/data_lineage.py | MEDIUM | 2 jam |
| 11 | Audit logger: log akses dashboard + query ke tabel audit_logs | src/governance/audit_logger.py | MEDIUM | 1.5 jam |

Cekpoint Day 4-5: RBAC bisa bedain role, audit log tercatat di PostgreSQL.

## Day 5-6: Storage (MinIO) + Settings

| No | Task | File | Prioritas | Estimasi |
| --- | --- | --- | --- | --- |
| 12 | MinIO client: upload frame metadata sebagai JSON ke MinIO bucket | src/storage/minio_client.py | LOW | 1.5 jam |
| 13 | Global settings: centralized config (threshold, interval, Kafka topics, dll) | src/config/settings.py | MEDIUM | 1 jam |

Cekpoint Day 5-6: MinIO bucket terisi data, settings bisa diakses dari mana aja.

## Day 6-7: Testing + Finalisasi

| No | Task | File | Prioritas | Estimasi |
| --- | --- | --- | --- | --- |
| 14 | Unit test alerting | tests/test_alerting.py | MEDIUM | 1.5 jam |
| 15 | Unit test governance | tests/test_governance.py | MEDIUM | 1.5 jam |
| 16 | Integrasi dashboard ML: tampilkan prediksi di Grafana sebagai timeseries tambahan | Grafana dashboard | HIGH | 2 jam |
| 17 | Final debug + push | - | HIGH | - |

# Timeline Visual 7 Hari

NAD

| Area | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Kafka | XXXX | - | - | - | - | - | - |
| Spark Str | - | XXXX | XXXX | - | - | - | - |
| Spark Bth | - | - | XXXX | XXXX | - | - | - |
| Airflow | - | - | - | XXXX | XXXX | - | - |
| Monitor | - | - | - | - | XXXX | XXXX | - |
| Integrasi | - | - | - | - | - | - | XXXX |

TAL

| Area | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ML | XXXX | XXXX | - | - | - | - | - |
| Grafana | - | XXXX | XXXX | - | - | - | - |
| Alerting | - | - | XXXX | XXXX | - | - | - |
| Sec/Gov | - | - | - | XXXX | XXXX | - | - |
| MinIO | - | - | - | - | XXXX | - | - |
| Testing | - | - | - | - | - | XXXX | XXXX |

# Daily Checkpoint

| Hari | Nad | Tal |
| --- | --- | --- |
| Day 1 | Kafka producer/consumer/test | ML clustering |
| Day 2 | Spark Streaming 2 query | ML clustering + forecasting start |
| Day 3 | Spark Streaming 4 query + Batch 2 | ML selesai + Grafana start |
| Day 4 | Batch 5 query + Airflow DAG 1 | Grafana selesai + Alerting start |
| Day 5 | Airflow 3 DAG + Docker | Alerting selesai + Security/Gov |
| Day 6 | Monitoring + Test detection | Security/Gov + MinIO + Test |
| Day 7 | Integrasi final + Push | Integrasi + Debug + Push |

# Important Notes

Prioritas utama: Spark Streaming (Nad) + ML (Tal) - ini core pipeline, kerjakan duluan.

Setiap selesai 1 file: test manual dulu sebelum lanjut ke file berikutnya.

Kalau stuck > 1 jam: tanya/tuker task yang lain dulu, jangan nunggu.

Commit tiap hari: jangan nunggu hari terakhir. Minimal 1 commit per hari.

Day 7 wajib full integrasi: gabungin semua komponen, fix error, pastikan flow end-to-end jalan.

Ceklist final: main.py -> Kafka -> Spark Streaming -> PostgreSQL -> Grafana dashboard -> alerting semua nyambung.